## Sheet1
WORKPLAN FOR THE IMPLEMENTATION OF iHRIS
No. | ACTIVITIES | BY WHEN | BY WHO | EXPECTED OUTPUT | INDICATORS | RISK ASSUMPTIONS | BUDGET
1 | Ministerial approval for use of iHRIS |  | HRH-TWG | Ministerial approval given. | Approval memo available. | Minister is politically disposed to approve and is available.
2 | Finalize compilation of standard lists for database. |  | HRH-TWG | Standard lists for database is compiled. | Proportion of number of expected lists compiled. | There is easy access to sources of the data to be compiled.
PILOT PHASE
3 | Data Collection at MOHSW: |  | HRIS-Team
| - Appoint coordinators for selected Departments |  | HRIS-Team | One coordinator appointed for each Dept. | Proportion of Dept that have selected coordinators. | Departments are willing to cooperate in the exercise.
| - Train coordinators on data collection form |  | HRIS-Team | All coordinators trained. | Proportion of coordinators that participated in the training. | Coordinators are willing and available to be trained.
| - Distribute data collection forms through Coordinators |  | HRIS-Team | All health workers received data collection forms. | Proportion of health workers in selected Departments that receive data collection forms. | Health workers willing to cooperate and complete the data form in the time frame given.
| - Collect completed data forms through coordinators and validate |  | HRIS-Team/HR Officers Personnel Unit | All health workers have completed and returned the data collection forms. All completed forms are validated for correctness of critical information. | Proportion of distributed forms which are completed and collected. Proportion of collected forms that are validated. | Coordinators are willing and available to collect completed forms from those they have them given to. Personnel Unit members are willing and available to validate all completed forms collected within the time frame given.
| - Recruit and train data entry clerks. |  | HRIS-Team | 6-10 data clerks recruited and trained. | No. of data clerks recruited and trained. | There are candidates qualified to be recruited as data clerks and those recruited are trainable to the level of competence demanded by the project.
| - Enter data from collected forms into the iHRIS system. |  | HRIS-Team/Data Clerks | All collected and validated forms are entered into the application - either as updates or fresh entry. | Proportion of collected and validated forms that are entered into the system. | Trained data clerks are competent enough to accurately (and with reasonable speed) enter the data from the forms into the application.
| - Create coded positions for the Officers whose data has been captured (updated or entered afresh) and assign positions to them. |  | HRIS-Team/Consultant | All staff captured have been assigned to their current positions. | Proportion of staff captured who have been assigned to their current positions. | The Job titles given in the data form corresponds to the titles in the CSA manual and the positions claimed by individuals in their forms exist in the organizational charts of the facilities or the Ministry.
| - Generate staffing reports from the system. |  | HRIS-Team/Consultant | Standard reports on the situation of Health Workers in the system are produced. | Proportion of standard reports in the system that were used to generate reports that could be used for decision making. | Enough data had been entered accurately into the system to enable the production of the required reports.
4 | Data Collection selected County(ies): |  | HRIS-Team/County HR Officers
| - Meet and brief County HR Officer(s). |  | HRIS-Team/County HR Officers | County HR officers adequately briefed about the project. | No. of HR officers briefed. Report of the briefing meeting available. | HR staff members of the iHRIS team are available for the briefing meeting(s) and County HR Officers are available also.
| - Appoint coordinators for selected Districts |  | HRIS-Team/County HR Officers | A coordinator is selected for each District. | Proportion of selected Districts in which coordinators were appointed. | Districts are willing to cooperate in the exercise and persons are available to be appointed as Coordinators.
| - Train coordinators on data collection form |  | HRIS-Team/County HR Officers | All coordinators trained. | Proportion of coordinators that participated in the training. | Coordinators are willing and available to be trained.
| - Distribute data collection forms through Coordinators |  | HRIS-Team/County HR Officers | All health workers in the Districts received data collection forms. | Proportion of health workers in selected Districts that receive data collection forms. | Health workers willing to cooperate and complete the data form in the time frame given.
| - Collect completed data forms through coordinators. |  | HRIS-Team/County HR Officers | All health workers have completed and returned the data collection forms. | Proportion of distributed forms which are completed and collected. | Coordinators are willing and available to collect completed forms from those they have them given to.
| - Collected data forms validated by County HR Officers and verified by Personnel Dept. |  | HRIS-Team/County HR Officers | All completed forms are validated for correctness of critical information. | Proportion of collected forms that are validated. | County HR Officers and Personnel Unit members are willing and available to validate all completed forms collected within the time frame given.
| - Enter data from collected forms into the iHRIS system. |  | HRIS-Team/Data Clerks | All collected and validated forms are entered into the application - either as updates or fresh entry. | Proportion of collected and validated forms that are entered into the system. | Trained data clerks are competent enough to accurately (and with reasonable speed) enter the data from the forms into the application.
| - Create coded positions for the Officers whose data has been captured (updated or entered afresh) and assign positions to them. |  | HRIS-Team/Consultant | All staff captured have been assigned to their current positions. | Proportion of staff captured who have been assigned to their current positions. | The Job titles given in the data form corresponds to the titles in the CSA manual and the positions claimed by individuals in their forms exist in the organizational charts of the facilities or the Ministry.
| - Generate staffing reports from the system. |  | HRIS-Team/Consultant | Standard reports on the situation of Health Workers in the system are produced. | Proportion of standard reports in the system that were used to generate reports that could be used for decision making. | Enough data had been entered accurately into the system to enable the production of the required reports.
5 | Review outcome of Pilot Phase. |  | HRH-TWG | Review meeting held. | Report of the review meeting available | All stakeholders are available to participate in the meeting.
6 | Make changes to the data collection form and data collection process if necessary. |  | HRIS-Team/Consultant | Data collection form and process updated as needed. | Proportion of recommended changes to the form and the process that are implemented. | Recommended changes are realistic and feasible.
7 | Compile list of additional reports required. |  | HRIS-Team/Consultant | List of additional reports compiled. | No. of new reports required. | HR Unit and Personnel Unit are available and have full comprehension of what is required.
8 | Create new reports. |  | HRIS-Team/Consultant | New reports created in the system. | Proportion of required reports that have been created. | Data elements required for creating reports have been captured in the system.
9 | Undertake further customization of the application if necessary. |  | HRIS-Team/Consultant | Application customized to meet new requirements. | No. of new fields and new modules created in the application. | The required customization is possible in the version of the iHRIS code available and in use in iHRIS-Manage-Liberia.
NATION-WIDE DEPLOYMENT PHASE
10 | Develop policy on use and access control. |  | HRH-TWG | Policy in place. | Copy of policy document available. | Responsible officers are available to draft the policy and the Minister is politically disposed and available to approve it.
11 | Train selected officers from Personnel and HR Units of MOHSW. |  | HRIS-Team/Consultant | All selected Officers trained. | No. of Selected Officers trained. | Selected Officers available and willing to be trained.
12 | Develop a work-plan for nation-wide deployment. |  | HRH-TWG | Work Plan developed. | Copy of work plan available. | Responsible officers are available to draft the work plan and the Minister is politically disposed and available to approve it.
13 | Train County HR Officers on iHRIS |  | HRIS-Team/Consultant | All County HR Officers trained. | No. of County HR officers trained. | County HR officers available and willing to be trained.
14 | Make iHRIS server accessible via the Internet. |  |  | iHRIS server can be accessed from all County offices in the country. | Proportion of counties with good and regular Internet connection to the Server. | MOHSW is able to obtain and finance a reliable ISP service for the iHRIS server and County offices have reliable and good connectivity to the Internet.
15 | Repeat activity (4) above in each County. |  | HRIS-Team/County HR Officers | (same as for activities 4 above) | (same as for activities 4 above) | (same as for activities 4 above)
16 | Train senior officers of MOHSW on use of iHRIS and use of data generated from it. |  | HRIS-Team/Consultant | All Senior Officers trained. | No. of Senior Officers trained. | Senior Officers available and willing to be trained.
17 | Launch the system officially. |  | HRH-TWG | Application is officially launched. | Report of the launch available. | Stakeholders are available and willing to participate.