## Doc Info
Document History
Ver. No. | Ver. Date | Prepared By | Reviewed By | Review Date | Affected Section & Summary of Change

## Sheet2 (hidden)
Issue ID | Project | Module | Issue Description/Activity | Expected Deliverables | Date Reported | (Days) | Start Date | Date End | Resource(s) | Progress Status | Actual Date Completed | Remarks | TBL Comments | Verification14/02/2013
130 | MIS | TDMS | Levy Return: Field for Visitors from Russia is missing on the input for in the system | Refer to Addendum | 2013-02-18 |  |  |  | TBL | CR |  |  | Not available in SRS | CR
89 | MIS | TDMS | Combine list of online and walk-in customers list and keep status as "Online", "Walk-in" for differentiating | Combine list of online and walk-in customers list and keep status as "Online", "Walk-in" for differentiating | 2013-02-01 | TBL | Pending |  | TBL | CR |  |  | CR | CR
88 | MIS | TDMS | Online levy: Keep status as "Verified" for cashier to see, after finance clerk has verified uploaded payment | Online levy: Keep status as "Verified" for cashier to see, after finance clerk has verified uploaded payment | 2013-02-01 | TBL | Pending |  | TBL | CR |  |  | CR | CR
87 | MIS | TDMS | Online levy form should go to finace clerk for verification, not registry. Finance role to be created for this purpose | Online levy form should go to finace clerk for verification, not registry. Finance role to be created for this purpose | 2013-02-01 | TBL | Pending |  | TBL | CR |  |  | CR | CR
86 | MIS | TDMS | System should not accept levy return if date of registration is later than effected date | System should not accept levy return if date of registration is later than effected date | 2013-02-01 | TBL | Pending |  | TBL | CR |  |  | CR | CR
83 | MIS | TDMS | Edit option after cashier has submited the levy return | Finace clerk should be able to edit the return after cashier has submitted | 2013-02-01 | TBL | Pending |  | TBL | CR |  |  | CR | CR
82 | MIS | TDMS | Levy effected date should not be a future date | Sytem should validate if future date is entered | 2013-02-01 | TBL | Pending |  | TBL | CR |  |  | CR | CR
81 | MIS | TDMS | Resitrict levy return year to current year | Resitrict levy return year to current year on the levy form | 2013-02-01 | TBL | Pending |  | TBL | CR |  | Return year should not be a future year, but it can be a past year | CR | CR
68 | MIS | TDMS | User Management on TDMS: Administrator cannot edit user details. It is only limited to delete. This is not appropriate user management | Employ standard user management principles | 2013-01-30 |  |  |  | TBL | CR |  | TBL was not agreed and not mentioned in new blue print about user management, System is following the old functionality | CR | CR
10 | MIS | TDMS | Letters are mal-aligned/formated and Enquiries Section missing on some letters | All letters from TDMS should bear an "Enquiries" section. 1. The name of the person for enquiries should the actual name of the user logged in (and not the login name) 2. The telephone number on the Enquiries section for all letters should be "+264 61 2906000" 3. The Fax number on the Enquiries section for all letters should be "+261 61 401401" 4. The email address of the Enquiries section should be populated from the email address of the user logged on | 2013-01-21 |  |  |  | TBL | CR |  | Soft copies of all letters were submitted with Highlightings of areas that should be populated automatically | CR, Format will be changed but getting logged in name automatically is CR | CR
67 | MIS | TDMS | User Management on TDMS: There is no search facility for the users list. | 1. For NTB users one should be able to search by username, firstname 2. For Online users one should be able to search by Trading Name, NTB Registration Number | 2013-01-30 |  |  |  | TBL | CR |  | Refer to Addendum Pg 61 | CR | CR
66 | MIS | TDMS | User Management on TDMS: There is no distinction between NTB users and Online (public) users | Online users are NTB Customers (Establishments and Businesses). There are approx 4000 of them who will potentially use the system! | 2013-01-30 |  |  |  | TBL | CR |  | System has to maintian two instances to separate users in the system,TBL was not agreed and not mentioned in new blue print about user management, System is following the old functionality | CR | CR
64 | MIS | TDMS | Ticking Forms pose a challenge in capturing for establishment with more rooms than can be accommodated in a single form (page) | Work around required | 2013-01-29 | TBL | Pending |  | TBL | CR |  | Alternative is to use and UPLOAD function to store Ticking Forms to the Library folder for the Customer. This is being suggested by Syntex as a work around to the current ticking forms in the system | CR | CR
63 | MIS | TDMS | Ticking Forms in the system have variations to the copies provided in the Initial Blueprint, in terms of content and form design | To verify Ticking Forms and ammend as per Initial Blueprint | 2013-01-29 | TBL | Pending |  | TBL,NTB | CR |  | Refer to Initial Blueprint Pg. 269-281. Discussion point with TBL | CR | CR
60 | MIS | TDMS | Star Grading: Process has been misunderstood for Pre-grading/Advisory/Mystery Guest, and Normal Grading | Applicant goes for pre-grading/advisory/mystery guest to assess readiness for Normal grading. If approved then customer can apply for Normal grading | 2013-01-29 | TBL | Pending |  | TBL | CR |  | What is present in the system is not as expected in practice. TBL claim to be a CR | CR | CR
59 | MIS | TDMS | spacing allignment in ticking forms to be corrected | spacing allignment in tikking forms to be corrected | 2013-01-29 |  |  |  | TBL | CR |  | How is this a CR? | CR | CR
57 | MIS | TDMS | System does not provide option to view Mystery Guest and Advisory Visit form at QM and SEISD level | User access to be created and form should be displayed | 2013-01-29 |  |  |  | TBL | CR |  | CR |  | CR
18 | MIS | TDMS | NTB request to view the uploaded documents when viewing the online application at registry level. (Currently the online application is viewed separately from the uploaded documents that are stored in the library | Provision of the facility | 2013-01-22 |  |  |  | TBL | CR | 2013-02-14 |  | CR | CR
28 | MIS | TDMS | NTB request to clear the Inspectors' screen after the approval of rejection. | As described | 2013-01-24 |  |  |  | TBL | CR |  |  | CR | CR
20 | MIS | TDMS | Users are unable to re-print certificates or discs in the event that there is a fault during printing. These are printed on pre-printed paper | System should provide for re-printing of certificates/discs by allowing users to manually enter the certificate/disc no before re-print. System should keep log of the voided certificate/disc | 2013-01-22 |  |  |  | TBL | CR | 2013-02-14 |  | CR | CR

## Sheet1 (hidden)
Issue ID | Project | Module | Issue Description/Activity | Expected Deliverables | Date Reported | (Days) | Start Date | Date End | Assigned to | Progress Status | Due Date | Remarks
15 | HRIS MAN | LMS | Update LMS User Manual | Updated LMS User Manual | 2013-06-17 |  |  |  | Leena | Open | 2013-06-28
14 | HRIS MAN | LMS | Movements Statistics Report | Review and restore functioning report | 2013-06-17 |  |  |  | Jason | Open | 2013-06-21
13 | HRIS MAN | LMS | Affirmative Action Report | Review and restore functioning report | 2013-06-17 |  |  |  | Leena | Open | 2013-06-21
12 | HRIS MAN | LMS | Retirement Report filters are not woking; ordering by date is not possible as date fields are of VARCHAR datatype | Review and rectify filters and restore ordering formats | 2013-06-17 |  |  |  | Jason | Open | 2013-06-21
10 | HRIS MAN | LMS | Review all reports | To Review all the reports deployed for LMS site | 2013-06-17 |  |  |  | Leena | Open
6 | HRIS MAN | LMS | Budget Summary & Detail Report to show only currency codes and only Filled positions | Resolve as described | 2013-03-22 |  |  |  | Jason | Open | 2013-06-21 | Technical issue with the database field. Its data type is "Currency" which carries both the number and the currency symbol. Need to convert the text field to number
7 | HRIS MAN | LMS | Salary field is not restricted to accept intergers only. Users can enter any character in the field | Salary field should not allow characters. | 2013-03-22 |  |  |  | Sam | Open | 2013-06-21 | Sam to follow up with ticket reaised on Google Group
8 | HRIS MAN | LMS | Unable to view changes made from screen "on View Recent Changes" form | Should display changes made Today, By Me or Anyone | 2013-03-22 |  |  |  | Jason | Open | 2013-06-21 | Jason to follow up with tickect raised on Google Group
9 | HRIS MAN | LMS | Search Staff Members form containes data list item "Namibia" which should not be in this form | Either remove it or edit it to an appropriate value | 2013-03-22 |  |  |  | Sam | Open | 2013-06-21 | Sam to follow up with ticket reaised on Google Group

## Sheet4 (hidden)
Issue ID | Project | Module | Issue Description/Activity | Expected Deliverables | Date Reported | (Days) | Start Date | Date End | Assigned to | Progress Status | Due Date | Remarks
1 | HRIS MAN | LMS | Reasons for Departure | Change the label to "Reasons for Movement" | 2013-03-22 |  |  |  | Sam | Closed | 2013-03-22
5 | HRIS MAN | LMS | Change Position Status from "Open" to "Vacant", and "Closed" to "Filled" | Change Position Status from "Open" to "Vacant", and "Closed" to "Filled" | 2013-03-22 |  |  |  | Jason | Closed | 2013-03-22
3 | HRIS MAN | LMS | Change the label "NAD N$" to use either NAD or N$ | On the Budget Reports (Summary and Detail), the currency indication should be either NAD or N$. This is mandatory | 2013-03-22 |  |  |  | Jason | Closed | 2013-03-22
4 | HRIS MAN | LMS | Change labels "Job Classifications" on Job Information form to "Occupation Classification" | Change labels "Job Classifications" to "Occupation Classification" | 2013-03-22 |  |  |  | Sam | Closed | 2013-03-22

## SUMMARY (hidden)
Count of Issue Description/Activity
Row Labels | Total
HRIS MAN | 15
LMS | 15
Closed | 15
Jason | 7
Leena | 2
Sam | 5
Jason, Bernard | 1
Grand Total | 15

## ISSUES
HRIS ISSUE MANAGEMENT LIST
[13 empty] | Last Updated: | 2014-02-25 12:31
[13 empty] | Priority Key: | 1 = High; 2= Medium; 3 = Low
Budgeted Duration
Issue ID | Project | Module | Object Type | Issue Description/Activity | Expected Deliverables | Date Reported | (Days) | Start Date | Date End | Assigned to | Progress Status | Due Date | Priority Scale | Remarks | Deploy?
1 | HRIS MAN |  | Report | Retirement Report filters are not woking; ordering by date is not possible as date fields are of VARCHAR datatype | Review and rectify filters and restore ordering formats | 2013-06-17 |  |  |  |  | Closed | 2013-07-02 | 1 | Used Dependancies function to convert the date format for display to the report. | Yes
2 | HRIS MAN |  | Form | Change label "Degree" to "Qualification" | From the initial list of customizations, we agreed to change the terminology for Degree, Education and Qualification to make more sense in the local context. The changes should be to: 1. Change Degree to Education type, e.g. Certificate, Diploma - this was done 2. Change Qualifications on View Person Information form to Professional memberships and Skills 3. Change Education History to Qualifications on view Person Information form 4. Change Degree Information to Qualification Information on Add/Update Education History form 5. Change Degree to Qualification on Add/Update Education History form 6. Change Add/Update Education History form to Add/Update Qualifications | 2013-03-22 |  |  |  |  | Closed | 2013-07-31 | 3 |  | Yes
3 | HRIS MAN |  | System | The current process of maintaining 2 different sites to ensure version control and that changes are tested before being moved to production is cumbersome and error-prone. | Using Launchpad to keep developer and production versions separately with a documented process. | 2013-06-24 |  |  |  |  | Closed | 2013-08-30 | 2

## Sheet3 (hidden)
TBL Comments | Verification14/02/2013
TBL Comments | Verification14/02/2013 | Closure Date
Closed | Verified
Closed
Closed | Verified
Closed | Verified
CR, Format will be changed but getting logged in name automatically is CR | CR
Closed | Verified
Closed | Verified
Closed | Closed/Not Verified
Not Possible | Not possible
Closed | Verified for Application/Registration/levy, Need to update for ther receipts in the system
Not Possible, it’s a manual process, system will not identify | Verified , Not possible
Closed | Verified
CR | CR
Closed | Verified
CR | CR
| Clarification, need to discuss with NAV | 21/02/2013
Closed | Closed/Not Verified
Closed | Verified
Closed | Verified
Closed | Verified
CR. Developed as per Forms given by NTB | Verified
Not Possible, Cashier will check manually with customer and take the payment, TDMS is not doing any payment validation | Not possible
CR | CR
Closed | Verified
Closed | Verified
Closed | Verified
Closed | Closed
Closed | Verified
Closed | Verified
Closed | Verified
Closed | Syntex team will update all pending users as per NTB inputs
30/01/2013
Closed | Verified
Closed | Verified, Developed as per disc given by NTB , NTb wants new format in new Disc, Waiting for new disc from NTB
Open | Verified, need to update in NAV database | 20/02/2013
2013-01-31
2013-01-30
2013-01-30
2013-01-30
Closed | Verified
closed | Verified
closed | Verified
CR
2013-01-31
2013-01-31
2013-01-31
2013-01-31
2013-01-31
2013-01-31
Issue | Verified
Issue | Verified
CR
Issue | Verified
CR | CR
CR | CR
Closed | Closed
CR | CR
CR | CR
CR | CR
Working fine , NTB users are not tested this process as they are not clear about this process | Verified
CR | CR
CR | CR
CR | CR
Issue | Verified
Verified
Closed | Verified
Issue | Verified
Closed. This would be covered as part of role configuration
Verified
CR | CR
CR | CR
CR | CR
Closed | Verified
Closed | Verified
CR | CR
CR | CR
CR | CR
CR | CR
Closed | Closed/Not Verified
Closed | Closed/Not Verified
Closed | Closed/Not Verified
Closed/Not Verified
| Open | 22/02/2013
Closed | Closed/Not Verified
| Open | 22/02/2013
Closed | Closed/Not Verified
Closed | Closed/Not Verified
Closed | Closed/Not Verified
Closed | Closed/Not Verified
Closed | Closed/Not Verified
Closed | Closed/Not Verified
Closed | Closed/Not Verified
Closed | Closed/Not Verified
Closed | Closed/Not Verified
| Open | 20/02/2013
Closed | Closed/Not Verified
Closed | Closed/Not Verified
Closed | Closed/Not Verified
Closed | Closed/Not Verified
| Open | 23/02/2013
Allignment is not done as we are waiting for new disc from NTB | Closed/Not Verified
Closed | Closed/Not Verified
Will be closed by 19-02-13
Will be closed by 19-02-13
Will be closed by 19-02-13
will be closed by 20-02-13
Not available in SRS | CR