## Sheet1
iHRIS Customization Plan
ID | % Complete | Task Name | Point Person | Duration | Start | Finish
1 |  | Project Initiation |  | 1 day
2 |  | Conduct Project Kick-Off Meeting |  | .5 days
3 |  | Presentation of Project Plan |  | .5 days
4 |  | IHRIS Demo |  | .5 days
5 |  | Conduct iHRIS Demo |  | .5 days
6 |  | Analysis Phase |  | 18.5 days
7 |  | Gather User Requirements
8 |  | HR Processes + Standard Data Lists |  | 3 days
9 |  | Reporting Requirements |  | 1 day
10 |  | User Requirements Documentation
11 |  | Compile User Requirements Document (URD) |  | 5 days
12 |  | URD Review (AMS) |  | 6 days
13 |  | URD Rework |  | 2 days
14 |  | URD Sign-Off |  | 0.5 days
15 |  | URD Printing and Binding |  | 1 day
16 |  | Development/Customization Phase |  | 45.5 days
17 |  | Confirm all Hardware and Related Software has been procured and commissioned |  | 0.5 days
18 |  | AMS Development/Test Site Configuration |  | 1 day
19 |  | Forms Customization of iHRIS for AMS
20 |  | Standard Master Data Forms (verified) |  | 2 days
21 |  | Salary Grades (Adopted for new Grade Structures) |  | 2 days
22 |  | Salary Notches for Grade (adopted for new Grades Structures) |  | 5 days
23 |  | Disciplinary Offences |  | 2 days
24 |  | Disciplinary Action (Action against given offence types) |  | 2 days
25 |  | Position |  | 2 days
26 |  | Establishment |  | 2 days
27 |  | Department and Sections |  | 2 days
28 |  | Leave Management |  | 5 days
29 |  | Training Module |  | 10 days
30 |  | Development of Custom AMS Reports |  | 10 days
31 |  | Testing Phase |  | 20.5 days
32 |  | Test the Customized iHRIS System |  | 13.5 days
33 |  | Compilation of Draft User Manual + UAT Test Scripts |  | 5 days
34 |  | Review of User Manual for AMS |  | 2 days